## Slide 1: Project Management Café
Insert client logo here
Notes: Facilitator notes:
Instructions: Proceed to the next slide once the presentation is visible to the participants.

## Slide 2: Welcome
(Please chat in to share your perspective)
“Project management is not new … While supervising the building of St. Peter’s Basilica in Rome, Michelangelo experienced all the torments of a modern-day project manager: incomplete specifications, insufficient labour, unsure funding, and a powerful customer. But only in the twentieth century did the title and the discipline emerge … Project management is the essential skill set for twenty-first century leaders.”
— Eric Verzuh, The Portable MBA in Project Management
Why has project management become the essential skill set for modern leaders?
Notes: Facilitator notes:
[Time: 2 min]
Say: Good morning/afternoon. This is ________ from ________. We’ll be starting today’s session at ___. As you come online, please take a moment to answer the question on your screen via the chat panel, “Why has project management become the essential skill for modern leaders.” We’ll give your colleagues a few more moments to join our session and then we’ll get started. Thank you.
Instructions: Consider answering the question in the chat panel first to show an example. Note: There is no need to debrief the question now—it will be discussed several slides later. Make note of the most common and least common responses so you are prepared to debrief later.

## Slide 3: Introductions
NAME
Title
NAME
Title
Notes: Facilitator notes:
[Time: 1 minute]
Instructions: Introduce yourself and any co-facilitator or web conferencing producer who might be helping with the session. Acknowledge the relative size of the audience and consider having participants chat in their locations if this information is not readily apparent. The point is to give people a sense of who is participating in the session today.

## Slide 4: Participation tips
Limit electronic interruptions.
Take part in the discussion.
Listen carefully to what is being said.
The CHAT PANEL is enabled for the session.
Use the RAISE HAND feature to volunteer to speak.
Put your phone on mute when not speaking.
CHAT
RAISE HAND
Notes: Facilitator notes:
[Time: 1 minute]
Say: Today’s session has been designed to be an interactive experience. To get the most from the session, here are a few tips about how to participate.
Instructions: Highlight any web conferencing features to be used, such as the chat panel and raise hand feature. Note that the raise hand feature may not be necessary if the group is relatively small. With a small group, participants could volunteer by simply unmuting themselves and speaking up. If you do choose to use the raise hand feature, explain, “When I invite you to raise your hand during the session, I mean you can click on the raise hand button if you want to share your thoughts with the group.”
Say: It appears we are ready to start.

## Slide 5: Setting the context
“Project management is not new … While supervising the building of St. Peter’s Basilica in Rome, Michelangelo experienced all the torments of a modern-day project manager: incomplete specifications, insufficient labour, unsure funding, and a powerful customer. But only in the twentieth century did the title and the discipline emerge … Project management is the essential skill set for twenty-first century leaders.”
— Eric Verzuh, The Portable MBA in Project Management
Why has project management become the essential skill set for modern leaders?
Notes: Facilitator notes:
[Time: 4 minutes]
Say: Projects are the means by which many vital ends are achieved in organizations. But project management isn’t a new concept. It has been around since ancient times. So why has project management become such an essential skill set for modern leaders?
You’ve shared some interesting perspectives on chat.
Instructions: Highlight responses, and call on 2-3 participants to expand on their answers.
Note: Experienced facilitators may wish to use the annotation feature to summarize responses in writing on the slide or using a whiteboard.
Say: Despite the fact that we’ve been managing projects for centuries and have a plethora of tools at our disposal, projects fail at an alarming rate: Research in some industries suggests that less than 20% of projects meet basic deliverables for time and budget. Why haven’t we learned to do it better? We are going to explore tools and strategies for improving our success rate today.

## Slide 6: Today’s objectives
Help you:
Define and manage scope
Effectively manage essential relationships
Monitor and manage milestones
Notes: Facilitator notes:
[Time: 1 minute]
Say: In a world where you cannot possibly plan for all of the variables you will face, an “adaptive” approach is necessary. Today’s session is focused on three important elements of project management:
Specifically, will will focus on how to:
Define and manage scope for both focus and flexibility
Effectively manage essential relationships, focusing on the team members over whom you have authority, and the various stakeholders over whom you have no authority and must leverage influence
Monitor and manage milestones, with particular emphasis on exploring strategies for getting a project back on track if it veers off course

## Slide 7
DEFINE AND MANAGE SCOPE
PROJECT
MANAGEMENT
Notes: Facilitator notes:
[Time: 1/2 minute]
Say: In a perfect world, project management would always be linear, with a simple problem to solve; a well-defined, stable scope; a well-understood technology infrastructure; low risks; and experienced project teams.
But in today’s complex business world, many projects don’t fall into this category. Instead:
The problems they seek to address don’t have known solutions
Project teams lack experience
Technologies are unfamiliar
So a successful project begins with a clearly defined scope that is flexible enough to respond to unforeseen events and equally focused on adhering to mission-critical goals and objectives.

## Slide 8: Define project scope
Tasks:
Define the problem
Identify stakeholders
Define objectives
Anticipate trade-offs (avoid scope creep)
Estimate project resources
  Which of these five key tasks in the planning phase is the most “predictable”? Which is potentially the most volatile and challenging to scope?
Notes: Facilitator notes:
[Time: 4 minutes]
Say: “Scope” refers to the project’s boundaries as determined by its goals and objectives. It is possibly the most critical part of the project, and the foundation for all other tasks – clarifying what the project will produce, when, and how much it costs.
To prepare for today’s session, you were asked to complete the tool “Worksheet for Clarifying Project Scope” in the “Establish Project Scope” lesson of the Harvard ManageMentor Project Management topic.
Say: Based on your experience using the tool and with other projects you have worked on, which of these five key tasks is the most “predictable” in the planning phase? Chat in the number 1 to 5.
  Instructions: After participants have chatted in their responses, annotate on the slide with a check mark or highlight to note the task that was voted the most predictable.
Say: Which is potentially the most volatile? Chat in the number 1 to 5.
  Instructions: After participants have chatted in their responses, annotate on the slide with a check mark or highlight to note the task that was voted the most volatile.
  Say: Thanks for sharing your perspectives. Let’s take a closer look at the challenges of establishing and managing project scope.

## Slide 9: Guard against “scope creep”
Have you experienced scope creep on a project?
What is one way to guard against scope creep on a project?
In your experience, why is establishing and maintaining scope so challenging?
Notes: Facilitator notes:
[Time: 5 minutes]
Say: With "scope creep," stakeholders pressure a project manager to do more than the project plan originally called for. If it’s not managed, scope creep can derail even the most well designed project.
Have you experienced scope creep on a project? Raise your hand if so.
Instructions: Count the raised hands and note the total, estimating a rough proportion of the total participants who have experienced it (e.g., nearly 100%, more than half).
Say: Whether you have personally experienced it or not, what is one way that you might guard against it? Chat in one suggestion.
Instructions: Allow about a minute for participants to chat in their suggestions for guarding against scope creep. Give 1-2 participants an opportunity to expand on their responses.
Say: Why is establishing and managing scope so challenging in your experience? Raise your hand if you have some thoughts to share.
Instructions: Give 1-2 people an opportunity to offer insights.

## Slide 10: Leverage a project charter
What key questions should your project charter address?
Notes: Facilitator notes:
[Time: 5.5 minutes]
Say: One of the most useful tools for helping to define project scope and manage scope creep is the project charter, which spells out the nature and scope of the work and expectations for results.
An effective project charter is a concise document containing answers to key questions about the problem you are trying to solve and the way you will go about solving it.
Ask: When you are establishing a project charter, what key questions must your charter address? Chat in 1-2 questions that you believe are critical to address in a project charter.
Instructions: Allow about a minute for participants to chat in answers to the question. Give an example from the list below if necessary to stimulate thinking. Highlight perspectives as they are shared.
Highlight the following questions if participants do not mention them:
  What business problem are we trying to solve?
  What are the parameters; i.e., what is in the scope of deliverables?
  What is not in scope for this project?
  What are stakeholders expecting to see as interim and final deliverables?
  What are the deadlines and milestones along the way?
  What assumptions are we making about this project’s feasibility?
  What risks are we likely to encounter?
  What resources will be available?

## Slide 11
MANAGE ESSENTIAL RELATIONSHIPS
PROJECT
MANAGEMENT
Notes: Facilitator notes:
[Time: 1/2 minute]
Say: A well-structured project charter is a key component of effective project management, but it is no substitute for effectively managing critical relationships. Let’s turn our attention to the people side of project management now.

## Slide 12: The six roles of a project team leader
Listener
Negotiator
Initiator
Worker/team member
Model
Coach
Notes: Facilitator notes:
[Time: 2 minutes]
Say: When you lead a project, you need to be as effective at managing people as you are at managing processes. To do this, you have to play many roles:
Initiator: Identify actions needed to meet project goals and encourage team members to take them
Model: Demonstrate behavior that supports the project's success
Negotiator: Use negotiating skills to obtain resources and to work with other project teams
Listener: Gather signals from the environment and make decisions informed by what you hear
Coach: Use motivational and developmental skills to help team members stay on task and excel in their roles
Working member of the team: Do a share of the work, particularly in areas where you have special competence
A critical and often overlooked task of a project manager is effectively managing relationships not only with the project team (over whom you often have authority) but also your stakeholders (over whom you often do not).
We’re going to spend some time now looking at the complex task of managing key stakeholder relationships.

## Slide 13: Identify stakeholders
Notes: Facilitator notes:
[Time: 4 minutes]
Say: To prepare for today’s session, you completed the practice activity “Attend to Stakeholders” in the “Communicate with Stakeholders” lesson of the Harvard ManageMentor Project Management topic.
You can’t build trust with a stakeholder unless you first know who he or she is. A stakeholder is a person, group, organization, member, or system who affects or can be affected by your – or your organization’s – actions. On a project, a stakeholder is anyone who has an interest in the project.
The slide describes some key stakeholder groups for business projects.
Say: Who are the key stakeholders you thought about as you undertook the practice activity? Chat in any who come to mind.
Instructions: Allow a minute for participants to chat in their responses. Briefly comment on the range (or similarity) of stakeholders across different projects, depending on participant replies.

## Slide 14: Attend to stakeholders
Critical actions | Strategies for improvement
Clearly articulate a plan that outlines how you will communicate with key stakeholders on a regular basis | 
Clearly identify project goals to all stakeholders | 
Alert all stakeholders to any changes and consequences, and verify that stakeholders accept responsibility for those consequences | 
Clarify assumptions about projected costs and completion dates | 
Keep communication ongoing and two-way | 
Notes: Facilitator notes:
[Time: 8.5 minutes]
Say: Thinking again about the practice activity, let’s consider how we might improve our stakeholder relationships. Here are some actions that are critical to effective stakeholder relationship management. Let’s consider them one at a time and identify improvements we might make in that area.
Instructions: Walk through the list of critical actions one at a time, and for each one, ask participants to identify strategies that would strengthen stakeholder relationships in that area, annotating responses on the slide.
Say, for example:
If we have not clearly articulated a plan that outlines how we will communicate with key stakeholders on a regular basis, what might we do to improve in this area?
How might we ensure that we have clearly identified project goals to all stakeholders?
How can we optimally alert all stakeholders to any changes and consequences and verified that stakeholders accept responsibility for those consequences?
What is one way that we might clarify assumptions about projected costs and completion dates?
How might we ensure that we keep communication ongoing and two-way?
Instructions: Use the chat feature to collect multiple responses or use the raise hand option and call on one person per question.
Say: Those are great suggestions. With your stakeholders on board and actively contributing, together you can focus your attention on managing the work according to the schedules, events, and milestones you’ve established.

## Slide 15
MONITOR AND MANAGE MILESTONES
PROJECT
MANAGEMENT
Notes: Facilitator notes:
[Time: 1/2 minute]
Say: Milestones are significant events in a project that remind team members of how far they’ve come and what they have yet to accomplish. We start measuring milestones from the moment we begin a project through to completion, which is the ultimate milestone. Project management and monitoring tools help us measure progress toward each milestone and to address any challenges that come up.

## Slide 16: Choose the right planning tool
Notes: Facilitator notes:
[Time: 5 minutes]
Say: The best tool for managing a project can often be the one you’re most comfortable with. Project managers often end up using different kinds of tools at different times, depending on whether they want to emphasize:
What has to be done
How long a particular activity will take
In what order each activity has to happen
Who is responsible for each activity
This slide highlights some of the most common project management planning tools:
Bar or Gantt charts are good for showing stakeholders and end users how the project is progressing.
Flow charts are good for closely managing and communicating detailed information to supervisors and people doing the work.
PERT charts are good for showing important task dependencies.
Ask: Which tools are the most commonly used in your group? Chat in any that you’ve used or seen.
Instructions: Allow participants a minute to review the slide and chat in responses. Highlight either their range or similarity as they come in.
Ask: What criteria might you use for choosing the right tool for your project? Chat in one criterion that you consider most critical.
Instructions: Call on 1-2 participants to comment if time permits.

## Slide 17: Monitor warning signs and keep on track
Indicators of trouble | Solutions for getting back on track
1. The team has spent more time on a key task than originally estimated | 
2. Scheduling problems have threatened the team’s ability to attain key milestones | 
3. Deliverables are meeting deadlines, but appear to be falling short of quality standards | 
4. Stakeholders are asking you to address more and more problems throughout the implementation of your project | 
5. Actual spending is higher than budgeted | 
Notes: Facilitator notes:
[Time: 5 minutes]
Say: As you implement your project, you will closely monitor the schedule, adjusting if conditions change. You will want to pay careful attention to warning signs that could reveal problems within your project team or difficulties with schedule, budget, or quality of your project’s outcomes.
Here are some common indicators of trouble in keeping a project on track. What others can you add to the list? Chat in any that come to mind.
Instructions: Ask participants to suggest additional signs, annotating them on the slide.
Say: Now let’s brainstorm some potential solutions for the problems you see most often. Which of the problems that we’ve highlighted do you encounter most often? Chat in the number.
Instructions: Give the participants a minute to chat in the number of the problem they encounter most frequently. Choose the top one or two problems and brainstorm solutions with the group.
Say: Thinking about this common problem, how might we address it? Raise your hand to suggest ways in which this problem can be overcome. Feel free to share any examples from your own experience or from other projects you’ve observed.
Say: Again, valuable suggestions. Let’s look at a situation now where many of these things are happening simultaneously and think about how we might deal with a total breakdown.

## Slide 18: Can this project be saved?
Dave is a management consultant at a midsize firm. His team has been assigned to work with an underperforming unit at a consumer goods company. The team will be conducting six weeks of analysis related to improving the company’s supply chain, then spend an additional 12 weeks helping the client implement the recommendations.
The team is five weeks into the assignment, and Dave is worried. The initial analysis has taken far longer than originally anticipated because the client has asked the team to interview more stakeholders and a visit to Chinese suppliers has been postponed. Several of Dave’s consultants have exceeded their expense budgets, an issue he surmises is due both to currency fluctuations and overspending.
Moreover, preliminary findings suggest the client’s supply chain will require far more “tweaking” to be effective than anticipated at the outset.
Dave has been in communication with his boss, who is aware of the issues. Now she has asked the question Dave has been asking himself: “Can we get the project back on track?”
What should Dave do?
SCENARIO
Notes: Facilitator notes:
[Time: 5 minutes]
Say: Take a minute to review this scenario, and then raise your hand to offer your perspective on what Dave should do.
Instructions: Give participants one minute to review the scenario, and then ask 2-3 participants to offer their perspectives. Highlight the following ideas if participants do not mention them:
Address scope creep issues, reminding stakeholders of contracted terms and/or discussing the possibility of extending the deadline.
Refer to the project charter or develop one based on contracted terms if it does not already exist.
Narrow the project scope, dropping nonessential elements of the project to save time.
Deploy more resources.
Clarify the expense policies and push back on authorized expenses.
Offer incentives to the team to encourage on-time delivery of needed resources or on-time completion of critical tasks.
Say: If you have been in a situation like this, you know how challenging it can be to get a project back on track. Once you've identified problems, however, you can work with your project team to figure out what’s causing the problems and take action together to address them. Raise your hands if you have been in a situation like this and have insights to share.
Instructions: If time permits, allow 1-2 participants to share personal insights or perspectives based on their experiences or perceptions.

## Slide 19
APPLY WHAT YOU’VE LEARNED
PROJECT
MANAGEMENT
Notes: Facilitator notes:
[Time: 1/2 minute]
Say: We’re coming to the end of our session today.

## Slide 20: Today’s objectives
Help you:
Define and manage scope
Effectively manage essential relationships
Monitor and manage milestones
  What will you take away from today’s session
  and apply to your role?
Notes: Facilitator notes:
[Time: 3 minutes]
Say: Today’s session focused on three important elements of project management. Specifically, we discussed how to:
Define and manage scope
Effectively manage essential relationships
Monitor and manage milestones
What is one insight that you will take away from today’s session and apply to your role? Raise your hand or chat in.
Instructions: Ask 2-3 participants to share an area of insight or idea.

## Slide 21: Apply what you’ve learned
Your next step is to complete the On-the-Job section of the Harvard ManageMentor Project Management topic.
Notes: Facilitator notes:
[Time: 1 minute]
Say: The next step for you in your development is to focus on applying and developing a skill that is particularly relevant to you, and has a good chance of making an impact in the workplace for you and your team.
The On-the-Job section in the Harvard ManageMentor Project Management topic provides an opportunity for you to pick a skill to work on and come up with specific ways to apply and develop the skill in your workplace. For instance, you can pick the skill: Assess and manage the risks that could derail projects I’m leading. Then you’ll identify specific action items that you can do to apply and develop this skill. For example, you could develop an action item of: “I will establish a project charter and use scheduling tools to monitor milestones and progress.”
Say: In order to complete this learning experience, proceed to the On-the-Job section in the Harvard ManageMentor topic. Remember, the only way to develop a skill is to apply and experiment with the use of that skill in your workplace.

## Slide 22: Thank you
Notes: Facilitator notes:
[Time: 1/2 minute]
Instructions: Thank participants for their time and active participation.